## Instructions
FLOSSLY TASKS - COMPREHENSIVE QA TESTING CHECKLIST
HOW TO USE THIS CHECKLIST:
1. This checklist contains 156 comprehensive test cases covering all aspects of Flossly Tasks
2. Test cases are organized by functional areas (Task Creation, Views, Collaboration, etc.)
3. Use the 'Pass_Fail' column to mark test results: PASS, FAIL, N/A, or BLOCKED
4. Document any issues or observations in the 'Notes' column
5. Priority levels indicate criticality: Critical > High > Medium > Low
COLOR CODING:
• Red background = Critical priority tests (must pass before release)
• Orange background = High priority tests (important for functionality)
• Yellow background = Medium priority tests (should work for good UX)
• White background = Low priority tests (nice-to-have features)
TESTING SECTIONS:
1. Core Task Management (Creation, Editing, Deletion, Assignment, Status)
2. Views & Organization (Board, List, Calendar)
3. Collaboration (Comments, File Attachments)
4. Search & Filtering
5. Bulk Operations
6. Permissions & Privacy
7. Notifications
8. Mobile & Performance
9. Archive & Data Management
TESTING TIPS:
• Test on multiple browsers: Chrome, Firefox, Safari, Edge
• Test on multiple devices: Desktop, tablet, mobile
• Test with different user roles: Owner, Manager, Staff, Receptionist
• Test with realistic data volumes (100+ tasks)
• Document all bugs with screenshots and steps to reproduce
COMPLETION TRACKING:
Total Test Cases: 156
Critical Priority: 43 tests
High Priority: 57 tests
Medium Priority: 41 tests
Low Priority: 15 tests
QA SIGN-OFF:
Tester Name: ___________________________
Test Date: ___________________________
Pass Rate: _____% (Passed / Total)
Ready for Production: ☐ Yes ☐ No
For questions or to report issues: support@flossly.com

## QA Test Cases
Section | Test_ID | Test_Case | Expected_Result | Pass_Fail | Notes | Priority
1.1 Task Creation | 1.1.1 | Create task with title with category | Task created successfully with status with category | 24.11.2025 | working | Critical
1.1 Task Creation | 1.1.2 | Create task with title + category - description | Both fields saved and displayed | 24.11.2025 | working | Critical
1.1 Task Creation | 1.1.3 | Create task with special characters in title | Title saves correctly with £, @, #, & symbols | 24.11.2025 | working | Medium
1.1 Task Creation | 1.1.4 | Create task with very long title (100+ characters) | Either truncates with warning or shows error | 24.11.2025 | "error message" showing | Low
1.1 Task Creation | 1.1.5 | Create task with emoji in title | Emoji displays correctly | 24.11.2025 | working | Low
1.1 Task Creation | 1.1.6 | Create blank task (no title) | System prevents or shows validation error | 24.11.2025 | working | Critical
1.1 Task Creation | 1.1.7 | Create task via quick-add button | Task created in current view/category | 24.11.2025 | working | High
1.1 Task Creation | 1.1.8 | Create task via '+' and an additional keyboard shortcut | Task creation modal opens | 24.11.2025 | working.. keyboard shortcut? | Medium
1.1 Task Creation | 1.1.9 | Create task and cancel | No task saved, modal closes | 24.11.2025 | working | Medium
1.1 Task Creation | 1.1.10 | Create multiple tasks rapidly (10 in 10 seconds) | All tasks created, no duplicates or crashes | 24.11.2025 | working (manually) | High
1.2 Task Editing | 1.2.1 | Edit task title | Changes save immediately or on blur | 24.11.2025 | glitch ( title only saves when changing the priority) | Critical
1.2 Task Editing | 1.2.2 | Edit task description | Description updates persist | 24.11.2025 | not working ( no option to edit this) | Critical
1.2 Task Editing | 1.2.3 | Edit task while another user is viewing- only happen when task is saved | No conflicts, updates visible to both users |  | n/a | High
1.2 Task Editing | 1.2.4 | Edit task from different device | Changes sync across devices |  | n/a | High
1.2 Task Editing | 1.2.5 | Edit task and press ESC | Changes cancelled, original text restored | 24.11.2025 | n/a | Medium
1.2 Task Editing | 1.2.6 | Edit task and navigate away | Prompt to save changes | 24.11.2025 | glitch ( only thing that works is "priority" & "frequency") | High
1.2 Task Editing | 1.2.7 | Add/remove tags | Tags update correctly | 24.11.2025 | n/a (tag meaning assign user?) | Medium
1.2 Task Editing | 1.2.8 | Change task color/label | Visual indicator updates | 24.11.2025 | working ( onlu "Priority" & "frequency" tab) | Low
1.2 Task Editing | 1.2.9 | Edit custom fields | Custom field values save | 24.11.2025 | working 90% (No option for "task description") | Medium
1.2 Task Editing | 1.2.10 | Undo/redo edits | Undo restores previous state | 24.11.2025 | n/a | Medium
1.3 Task Deletion | 1.3.1 | Delete single task | Confirmation modal appears | 24.11.2025 | working | Critical
1.3 Task Deletion | 1.3.2 | Confirm task deletion | Task removed from list | 24.11.2025 | working | Critical
1.3 Task Deletion | 1.3.3 | Cancel task deletion - Archieve | Task remains, modal closes | 24.11.2025 | glitch( once archieved,it still shows on task list) | New Feature
1.3 Task Deletion | 1.3.4 | Delete task with subtasks | Option to delete all or keep subtasks | 24.11.2025 | n/a | New Feature
1.3 Task Deletion | 1.3.5 | Delete task with comments | All comments deleted with task | 24.11.2025 | glitch ( after deleting and submitting information, it doesn't disappear) | Medium
1.3 Task Deletion | 1.3.6 | Delete task with attachments | Files deleted or archived | 24.11.2025 | Glitch (unable to delete file or download it) | Medium
1.3 Task Deletion | 1.3.7 | Restore deleted task (soft delete) | Task moved to trash/archive | 24.11.2025 | n/a | New Feature
1.3 Task Deletion | 1.3.8 | Permanently delete task | Task removed from database | 24.11.2025 | n/a | New Feature
1.3 Task Deletion | 1.3.9 | Bulk delete multiple tasks | Confirmation for bulk action, all tasks deleted | 24.11.2025 | working | High
1.3 Task Deletion | 1.3.10 | Delete task created by another user | Permissions checked, only authorized users can delete |  |  | Critical
1.4 Task Assignment | 1.4.1 | Assign task to single user | User assigned, notification sent |  |  | Critical
1.4 Task Assignment | 1.4.2 | Assign task to multiple users | All users assigned and notified |  |  | High
1.4 Task Assignment | 1.4.3 | Reassign task from User A to User B | User A removed, User B added, both notified |  |  | High
1.4 Task Assignment | 1.4.4 | Unassign task | Task returns to unassigned state |  |  | Medium
1.4 Task Assignment | 1.4.5 | Assign to deactivated user | System prevents or shows warning |  | n/a | New Feature
1.4 Task Assignment | 1.4.6 | Assign to user from different practice (multi-tenant) | System prevents (privacy control) |  |  | Critical
1.4 Task Assignment | 1.4.7 | Assign to self | User can self-assign tasks |  |  | Medium
1.4 Task Assignment | 1.4.8 | View all tasks assigned to specific user | Filter works correctly |  | happen through filter | High
1.4 Task Assignment | 1.4.9 | Assignee dropdown shows correct staff list | Only active staff from current practice shown |  |  | Critical
1.4 Task Assignment | 1.4.10 | Assignee receives notification | Email/push notification sent |  |  | High
Mandatory task must show when loggin in - based on role
1.5 Task Status & Workflow | 1.5.1 | Change status: To Do → In Progress | Status updates, visual indicator changes |  |  | Critical
1.5 Task Status & Workflow | 1.5.2 | Change status: In Progress → Completed | Status updates, task marked complete |  |  | Critical
1.5 Task Status & Workflow | 1.5.3 | Change status: To Do → Completed (direct) | Allowed, no forced intermediary steps |  |  | Critical
1.5 Task Status & Workflow | 1.5.4 | Change status: Completed → In Progress (reopen) | Task reopened successfully |  |  | High
1.5 Task Status & Workflow | 1.5.5 | Add Status Button | Add status button on the coloumn section |  |  | High
1.5 Task Status & Workflow | 1.5.6 | Drag task between status columns (Kanban) | Status updates when moved |  |  | New feature
1.5 Task Status & Workflow | 1.5.7 | Status change triggers automation | notification to be recieved |  |  | Medium
1.5 Task Status & Workflow | 1.5.8 | Completed tasks auto-archive after 5 days | Archive automation works |  |  | High
1.5 Task Status & Workflow | 1.5.9 | View tasks by status filter | Filter shows correct tasks |  |  | High
1.5 Task Status & Workflow | 1.5.10 | Status history/audit trail | Previous statuses logged |  |  | New Feature
2.1 Board View (Kanban) | 2.1.1 | Switch to Board view | Kanban board displays |  |  | New Feature
2.1 Board View (Kanban) | 2.1.2 | Columns represent task statuses | To Do, In Progress, Completed columns visible |  |  | Critical
2.1 Board View (Kanban) | 2.1.3 | Drag task between columns | Task status updates, visual feedback shown |  |  | Critical
2.1 Board View (Kanban) | 2.1.4 | Drag task within same column (reorder) | Task order changes |  |  | Medium
2.1 Board View (Kanban) | 2.1.5 | Add new column | Custom status column created |  |  | New Feature
2.1 Board View (Kanban) | 2.1.6 | Rename column | Column name updates |  |  | Low
2.1 Board View (Kanban) | 2.1.7 | Delete column - design must be adjusted | Tasks moved or deleted, column removed |  |  | High
2.1 Board View (Kanban) | 2.1.8 | Collapse/expand column | Column minimizes/expands |  |  | Low
2.1 Board View (Kanban) | 2.1.9 | Task count per column | Number of tasks displayed in column header |  | on the main dashboard | Low
2.1 Board View (Kanban) | 2.1.10 | Click task card | Only Animation |  |  | Critical
2.2 List View | 2.2.1 | Switch to List view, calender view | Tasks displayed in list format |  |  | Critical
2.2 List View | 2.2.2 | Columns: Title, Assignee, Due Date, Priority, Status | All columns visible - based on clicking on coloumn list |  |  | High
2.2 List View | 2.2.3 | Sort by Title (A-Z) | Tasks sorted alphabetically |  |  | High
2.2 List View | 2.2.4 | Sort by Due Date (earliest first) | Tasks sorted by date |  |  | High
2.2 List View | 2.2.5 | Sort by Priority (High to Low) | High priority tasks first |  |  | High
2.2 List View | 2.2.6 | Customize visible columns | Show/hide columns works |  |  | Medium
2.2 List View | 2.2.7 | Reorder columns | Drag column headers to reorder |  |  | Low
2.2 List View | 2.2.8 | Resize columns | Column width adjustable |  |  | Low
2.2 List View | 2.2.9 | Select all tasks in list | Checkbox selects all visible tasks |  |  | Critical
2.3 Calendar View | 2.3.1 | Switch to Calendar view | Calendar displays with tasks |  |  | Critical
2.3 Calendar View | 2.3.2 | Tasks appear on due date | Tasks visible on correct dates |  |  | Critical
2.3 Calendar View | 2.3.3 | Day view shows all tasks for that day | All tasks listed |  |  | New Feature
2.3 Calendar View | 2.3.4 | Week view shows 7-day overview | Week grid displays |  |  | New Feature
2.3 Calendar View | 2.3.5 | Month view shows full month | Month grid displays |  |  | New Feature
2.3 Calendar View | 2.3.6 | Navigate: Previous/Next month | Calendar updates |  |  | Medium
2.3 Calendar View | 2.3.7 | Click date to create task on that date | Task creation modal opens with date pre-filled |  |  | New Feature
2.3 Calendar View | 2.3.8 | Drag task to different date | Due date updates- calendar view |  |  | New Feature
2.3 Calendar View | 2.3.9 | Color-code tasks by priority/category | Visual differentiation works |  |  | Medium
2.3 Calendar View | 2.3.10 | Today's date highlighted | Current day visually distinct |  |  | Low
3.1 Comments & Activity | 3.1.1 | Add comment to task | Comment saves and displays |  |  | Critical
3.1 Comments & Activity | 3.1.2 | Add comment with @mention | User tagged receives notification |  |  | New Feature
3.1 Comments & Activity | 3.1.4 | Add comment with link | Link is clickable |  |  | New Feature
3.1 Comments & Activity | 3.1.5 | Edit own comment | Comment updates |  |  | Medium
3.1 Comments & Activity | 3.1.6 | Delete own comment | Comment removed |  |  | Medium
3.1 Comments & Activity | 3.1.7 | Reply to comment (threaded) | Reply nested under original |  |  | New Feature
3.1 Comments & Activity | 3.1.8 | View comments in chronological order | Newest first or oldest first |  |  | Low
3.1 Comments & Activity | 3.1.9 | Like/react to comment | Reaction recorded |  |  | New Feature
3.1 Comments & Activity | 3.1.10 | Real-time comment updates | New comments appear without refresh |  | aqib to design screen | New Feature
3.2 File Attachments | 3.2.1 | Upload file via drag & drop | File uploads successfully |  |  | Critical
3.2 File Attachments | 3.2.2 | Upload file via browse button | File uploads successfully |  |  | Critical
3.2 File Attachments | 3.2.3 | Upload multiple files at once | All files upload |  |  | High
3.2 File Attachments | 3.2.4 | Upload large file (>5MB) | Shows progress bar, uploads or shows size limit |  |  | High
3.2 File Attachments | 3.2.5 | Upload common file types (PDF, DOCX, PNG, JPG) | All formats accepted |  |  | High
3.2 File Attachments | 3.2.6 | Upload restricted file type (.exe) | System rejects with error |  |  | Critical
3.2 File Attachments | 3.2.7 | View attached file thumbnail | Preview shows for images |  |  | Low
3.2 File Attachments | 3.2.8 | Download attached file | File downloads correctly |  |  | Critical
3.2 File Attachments | 3.2.9 | Delete attached file | File removed from task |  |  | Medium
3.2 File Attachments | 3.2.10 | File size shown for each attachment | Size displayed (e.g., 2.5 MB) |  |  | Low
4.1 Search Functionality | 4.1.1 | Search by task title | Matching tasks displayed |  |  | Critical
4.1 Search Functionality | 4.1.2 | Search by keyword in description | Tasks with keyword in description shown |  |  | High
4.1 Search Functionality | 4.1.3 | Search by assignee name | All tasks assigned to that person shown |  |  | High
4.1 Search Functionality | 4.1.4 | Search by tag | Tasks with specific tag shown |  |  | Medium
4.1 Search Functionality | 4.1.5 | Search with partial match | 'comp' finds 'Compliance Audit' |  |  | High
4.1 Search Functionality | 4.1.6 | Search with no results | 'No tasks found' message shown |  |  | Low
4.1 Search Functionality | 4.1.7 | Real-time search (as you type) | Results update instantly |  |  | Medium
4.1 Search Functionality | 4.1.8 | Clear search | All tasks reappear |  |  | Medium
4.2 Filtering | 4.2.1 | Filter by status (To Do only) | Only To Do tasks shown |  |  | Critical
4.2 Filtering | 4.2.2 | Filter by assignee | Tasks assigned to selected user shown |  |  | High
4.2 Filtering | 4.2.3 | Filter by priority | Only High priority tasks shown |  |  | High
4.2 Filtering | 4.2.4 | Filter by due date: Overdue | Overdue tasks shown |  |  | Critical
4.2 Filtering | 4.2.5 | Filter by due date: Due today | Today's tasks shown |  |  | High
4.2 Filtering | 4.2.6 | Filter by due date: Due this week | Next 7 days shown |  |  | High
4.2 Filtering | 4.2.7 | Filter by category/project | Tasks in that category shown |  |  | High
4.2 Filtering | 4.2.8 | Combine multiple filters | AND logic applied (status + assignee) |  |  | High
4.2 Filtering | 4.2.9 | Save filter as custom view | Filter saved for reuse |  |  | Medium
4.2 Filtering | 4.2.10 | Clear all filters | All tasks reappear |  |  | Medium
5.1 Bulk Selection & Actions | 5.1.1 | Select all tasks (checkbox) | ALL visible tasks selected |  |  | Critical
5.1 Bulk Selection & Actions | 5.1.2 | Bulk change status | All selected tasks update status |  |  | New Feature
5.1 Bulk Selection & Actions | 5.1.3 | Bulk change assignee | All selected tasks reassigned |  |  | New Feature
5.1 Bulk Selection & Actions | 5.1.4 | Bulk change due date | All selected tasks get new due date |  |  | New Feature
5.1 Bulk Selection & Actions | 5.1.5 | Bulk change priority | All selected tasks update priority |  |  | New Feature
5.1 Bulk Selection & Actions | 5.1.6 | Bulk delete tasks | Confirmation shown, all tasks deleted |  |  | Critical
5.1 Bulk Selection & Actions | 5.1.7 | Bulk archive tasks | All tasks moved to archive |  |  | High
5.1 Bulk Selection & Actions | 5.1.8 | Bulk export tasks | CSV/Excel export of selected tasks |  |  | Medium
Add a delete button on bulk upload task
6.1 Role-Based Access Control | 6.1.1 | Practice Owner can see all tasks | Full visibility |  |  | Critical
6.1 Role-Based Access Control | 6.1.2 | Practice Manager can see all tasks | Full visibility |  |  | Critical
6.1 Role-Based Access Control | 6.1.3 | Staff member sees only assigned tasks | Limited visibility |  |  | Critical
6.1 Role-Based Access Control | 6.1.4 | Receptionist cannot see confidential tasks | Privacy enforced |  |  | Critical
6.1 Role-Based Access Control | 6.1.5 | Create private category (Manager only) | Category hidden from staff- any task category created should not show up on task pool |  | TaskPool - Workflows with Tasks - RECOMMENDED | Critical
6.1 Role-Based Access Control | 6.1.6 | Multi-practice isolation | Practice A cannot see Practice B tasks |  |  | Critical
6.1 Role-Based Access Control | 6.1.7 | Non-admin cannot delete others' tasks | Permission denied |  |  | High
7.1 Email & In-App Notifications | 7.1.1 | Task assigned notification | Email notification sent |  |  | High
7.1 Email & In-App Notifications | 7.1.2 | Task due tomorrow reminder | Reminder email sent |  |  | High
7.1 Email & In-App Notifications | 7.1.3 | Comment added notification | Notification to assignee/watchers |  |  | Medium
7.1 Email & In-App Notifications | 7.1.4 | @mention notification | User receives notification |  |  | High
7.1 Email & In-App Notifications | 7.1.5 | In-app notification bell | Badge displays number of unread |  |  | Medium
7.1 Email & In-App Notifications | 7.1.6 | Click notification | Navigates to relevant task |  |  | High
7.1 Email & In-App Notifications | 7.1.7 | Customize notification settings | User can choose which notifications to receive |  |  | Medium
8.1 Mobile Responsiveness | 8.1.1 | Open on mobile browser | Layout adapts to screen |  |  | Critical
8.1 Mobile Responsiveness | 8.1.2 | Navigation menu accessible | Hamburger menu works |  |  | Critical
8.1 Mobile Responsiveness | 8.1.3 | Create task on mobile | Touch-friendly form |  |  | High
8.1 Mobile Responsiveness | 8.1.4 | Upload file on mobile | Camera/gallery access works |  |  | Medium
8.1 Mobile Responsiveness | 8.1.5 | Swipe gestures | Swipe to complete/delete works |  |  | Medium
8.2 Performance | 8.2.1 | Dashboard loads in <2 seconds | Fast initial load |  |  | High
8.2 Performance | 8.2.2 | Task list with 100 tasks loads in <1 second | Quick rendering |  |  | High
8.2 Performance | 8.2.3 | Search returns results in <500ms | Fast search |  |  | High
8.2 Performance | 8.2.4 | 10 users editing simultaneously | No conflicts, all changes save |  |  | High
9.1 Archive & Export | 9.1.1 | Manually archive completed task | Task moves to Archive |  |  | Critical
9.1 Archive & Export | 9.1.2 | Auto-archive tasks completed >30 days ago | Automation works |  |  | High
9.1 Archive & Export | 9.1.3 | Access Archive tab | Archived tasks visible |  |  | High
9.1 Archive & Export | 9.1.4 | Restore archived task | Task returns to active list |  |  | Medium
9.1 Archive & Export | 9.1.5 | Export tasks to CSV | File downloads with all task data |  |  | Medium
9.1 Archive & Export | 9.1.6 | Export tasks to Excel | Excel file opens correctly |  |  | New Feature

## Bug Tracking List
Bug ID | Bug Title | Description | Severity | Category | Status
BUG-001 | Task Pool Contamination | Custom categories/tabs incorrectly appear in Task Pool, mixing templates with user-created categories | Critical | Task Pool | Open
BUG-002 | Task Status Workflow Broken | Tasks cannot be marked as complete directly; users must mark them pending first | Critical | Workflow | Open
BUG-003 | Bulk Selection Fails | 'Select All' doesn't select all tasks—only a subset is included in bulk actions | Critical | Bulk Operations | Open
BUG-004 | Duplicate Categories on Creation | Creating a new category results in multiple duplicate categories appearing | Critical | Categories | Open
BUG-005 | Incorrect Team Members Shown | Assign dropdown includes wrong staff (other practices, deactivated, missing current staff) | Critical | Assignment | Open
BUG-006 | Confidential Categories Insecure | Confidential/private categories visible to all staff regardless of permissions | Critical | Privacy | Open
BUG-007 | Cannot Assign Tasks to Team | Task assignment/delegation to team members doesn't work | Critical | Assignment | Open
BUG-008 | Archive Functionality Missing | Completed tasks do not move to archive and continue cluttering active lists | High | Archive | Open
BUG-009 | Category Creation Fails Silently | Sometimes, creating a category does nothing—no error or feedback shown | High | Categories | Open
BUG-010 | Comments/Notes Don't Save | Comments added to tasks disappear or don't persist after page refresh | High | Collaboration | Open
BUG-011 | No Task Search Functionality | Users lack a search bar—must scroll manually to find tasks | High | Search | Open
BUG-012 | No Due Date Filtering | Cannot filter tasks by due date or quickly view overdue/urgent tasks | High | Filtering | Open
BUG-013 | No Mobile App/Not Responsive | Mobile version is missing or web app is not usable on phones/tablets | High | Mobile | Open
BUG-014 | No Activity Log/Audit Trail | No visible record of who acted on a task and when | High | Audit | Open
BUG-015 | No Recurring Tasks | Tasks cannot be set to repeat daily/weekly/monthly; must recreate manually | High | Features | Open
BUG-016 | Missing Status Tab/Filter | No tab or filter to view and organize tasks by status (To Do, In Progress, Completed) | Medium | UI/UX | Open
BUG-017 | No Task Priority Indicator | No visual marker for task urgency/priority (high/medium/low not displayed) | Medium | UI/UX | Open
BUG-018 | File Upload Issues | Task file uploads are unreliable—files don't appear, fail without feedback, can't delete | Medium | Files | Open
BUG-019 | No Email Notifications | Users get no notifications for assignments, comments, or changes | Medium | Notifications | Open
BUG-020 | No Task Dependencies | Cannot link tasks so that one depends on the completion of another | Medium | Features | Open
BUG-021 | Can't Save Custom Task Templates | Users can't save frequent workflows as reusable templates | Medium | Templates | Open
BUG-022 | No Time Tracking | No feature to track or log time spent on tasks | Low | Features | Open
BUG-023 | No Integrations | No capability to integrate with calendars, emails, or third-party tools | Low | Integrations | Open